## CLIENT_SUMMARY
| Client Name |  | Energy Transfer | [5 empty] | LEGEND
| Project Name |  | This Meter Station | [6 empty] | Changes made to this revison
| Revision |  | 2013-07-03 - 02:31:28 PM
| HMM Contact |  | Olin Valby - 281-598-9539
Current Quantities Per Site | [10 empty] | Material Requested
Client No. | Mark No. | Unit | Description | Uniontown | Site A | Parker | Fab AB | Consumables | Total Qty. | Quantity Left to Acquire | Total Inventory to Date | UNTWN2 | BRDLAND | TST1234 | RFRP1234 | 123258 | Previous 0 RFP(s)
[12 empty] | 2013-07-03 | 2013-06-06 | 2013-05-08 | 2013-05-01 | 2013-04-22 | 2013-04-22
| 1 | FT | PIPE - 30", 0.500" WT, ERW/DSAW, BE, API 5L PSL-2, X65, BARE |  | 2 | 5 |  | 0 | 7 | 0 | 7 |  |  | 2
| 3 | FT | PIPE - 24", 0.500" WT, ERW/DSAW, BE, API 5L PSL-2, X60, BARE | 17 |  |  |  | 0 | 17 | 0 | 17 |  |  | 17
| 4 | FT | PIPE - 20", 0.500" WT, ERW/DSAW, BE, API 5L PSL-2, X60, BARE |  |  | 18 |  | 0 | 18 | 1 | 17 |  | 17
| 5 | FT | PIPE - 16", 0.500" WT, ERW/DSAW, BE, API 5L PSL-2, X52, BARE | 19 | 21 | 19 |  | 0 | 59 | 0 | 59 |  | 19 | 19 | 21
| 7 | FT | PIPE - 12", 0.375" WT, ERW/SMLS, BE, API 5L PSL-2, X52, BARE | 15 | 25 | 17 |  | 2 | 59 | 0 | 59 |  | 17 | 17 | 25
| 8 | FT | PIPE - 12", 0.375" WT, ERW/SMLS, BE, API 5L PSL-2, X52, COATED | 113 |  | 113 |  | 0 | 226 | 0 | 226 |  | 111 | 115
| 9 | FT | PIPE - 10", 0.365" WT, ERW/SMLS, BE, API 5L PSL-2, X52, BARE | 29 |  | 29 |  | 20 | 78 | 3 | 75 | 39
| 11 | FT | PIPE - 10", 0.322" WT, ERW/SMLS, BE, API 5L PSL-2, X42, COATED |  |  |  | 80 | 0 | 80 | 12 | 68 |  |  |  |  | 60
| 12 | FT | PIPE - 8", 0.322" WT, ERW/SMLS, BE, API 5L PSL-2, X42, BARE | 1 | 5 | 1 |  | 0 | 7 | -37 | 44 |  |  |  | 5 | 39
| 13 | FT | PIPE - 8", 0.322" WT, ERW/SMLS, BE, API 5L PSL-2, X42, COATED | 6 |  | 6 |  | 0 | 12 | 0 | 12 | 6 | 6
| 14 | FT | PIPE - 6", 0.280" WT, ERW/SMLS, BE, API 5L PSL-2, GRB, BARE | 3 |  | 3 |  | 0 | 6 | 0 | 6 |  | 3 | 3
| 15 | FT | PIPE - 6", 0.280" WT, ERW/SMLS, BE, API 5L PSL-2, GRB, COATED | 29 |  | 29 |  | 0 | 58 | 0 | 58 |  | 29 | 29
| 16 | FT | PIPE - 4", 0.237" WT, ERW/SMLS, BE, API 5L PSL-2, GRB, BARE | 13 | 84 | 13 |  | 0 | 110 | -10 | 120 |  | 13 | 13 | 84
| 17 | FT | PIPE - 4", 0.237" WT, ERW/SMLS, BE, API 5L PSL-2, GRB, COATED |  | 17 |  |  | 0 | 17 | -17 | 34 |  |  |  | 17 | 17
| 18 | FT | PIPE - 2", 0.218" WT, ERW/SMLS, BE, API 5L PSL-1, GRB, BARE | 4 | 51 | 4 |  | 0 | 59 | 0 | 59 |  | 4 | 4 | 51
| 19 | FT | PIPE - 1 1/2", 0.200" WT, SMLS, BE, ASTM A106, GRB, BARE | 14 |  | 14 |  | 0 | 28 | 0 | 28 |  | 14 | 14
| 20 | FT | PIPE - 1", 0.179" WT, SMLS, BE, ASTM A106, GRB, BARE | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 21 | FT | PIPE - 3/4", 0.154" WT, SMLS, BE, ASTM A106, GRB, BARE | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 22 | FT | PIPE - 1/2", 0.147" WT, SMLS, BE, ASTM A106, GRB, BARE | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 45 | EA | FLANGE - 16", ANSI 600, RFWN, ASTM A694, F52, TWT 0.500" WT, X52 PIPE, PER MSS-SP-44 | 4 |  | 4 |  | 0 | 8 | 0 | 8 |  |  | 4 | 4
| 46 | EA | FLANGE - 12", ANSI 600, RFWN, ASTM A694, F52, TWT 0.375" WT, X52 PIPE, PER MSS-SP-44 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 47 | EA | FLANGE - 10", ANSI 600, RFWN, ASTM A694, F52, TWT 0.365" WT, X52 PIPE, PER MSS-SP-44 | 4 |  | 4 |  | 0 | 8 | 0 | 8 |  |  | 4 | 4
| 48 | EA | FLANGE - 8", ANSI 600, RFWN, ASTM A694, F42, TWT 0.322" WT, X42 PIPE, PER MSS-SP-44 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 49 | EA | FLANGE - 6", ANSI 600, RFWN, ASTM A105, GR B, TWT 0.280" WT, GR B PIPE, PER ASME B16.5 | 4 |  | 4 |  | 0 | 8 | 0 | 8 |  |  | 4 | 4
| 50 | EA | FLANGE - 4", ANSI 600, RFWN, ASTM A105, GR B, TWT 0.237" WT, GR B PIPE, PER ASME B16.5 | 3 |  | 3 |  | 0 | 6 | 0 | 6 |  |  | 3 | 3
| 51 | EA | FLANGE - 2", ANSI 600, RFWN, ASTM A105, GR B, TWT 0.218" WT, GR B PIPE, PER ASME B16.5 | 7 |  | 7 |  | 0 | 14 | 0 | 14 |  |  | 7 | 7
| 52 | EA | FLANGE - 1 1/2", ANSI 600, RFWN, ASTM A105, GR B, TWT 0.200" WT, GR B PIPE, PER ASME B16.5 | 6 |  | 6 |  | 0 | 12 | 0 | 12 |  |  | 6 | 6
| 53 | EA | FLANGE, BLIND - 8", ANSI 600, RF, ASTM A694, F52, MSS SP-44, CD&T FOR 1" NPT |  | 5 |  |  | 0 | 5 | 5 | 0
| 54 | EA | FLANGE, BLIND - 2", ANSI 600, RF, ASTM A105, GR B, PER ASME B16.5, CD&T FOR 1/2" NPT | 3 |  | 3 |  | 0 | 6 | 0 | 6 |  |  | 3 | 3
| 23 | EA | TEE, STRAIGHT - 12", 0.375" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 24 | EA | TEE, STRAIGHT - 10", 0.365" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 26 | EA | TEE, REDUCING - 16", 0.500" WT x 12", 0.375" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 27 | EA | TEE, REDUCING - 12", 0.375" WT x 6", 0.280" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 1 | 1 |  |  | 1
| 28 | EA | TEE, REDUCING - 12", 0.375" WT x 4", 0.237" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 29 | EA | TEE, REDUCING - 8", 0.322" WT x 6", 0.280" WT, BW, MSS-SP-75, Y42, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 39 | EA | REDUCER, CONC. - 20", 0.500" WT x 16", 0.375" WT, BW, MSS-SP-75, Y60, PER ASME B16.9 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 40 | EA | REDUCER, CONC. - 12", 0.375" WT x 10", 0.365" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 41 | EA | REDUCER, CONC. - 12", 0.375" WT x 8", 0.322" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 43 | EA | REDUCER, CONC. - 6", 0.280" WT x 4", 0.237" WT, BW, ASTM A234, WPB, PER ASME B16.9 |  |  |  |  | 0 | 0 | -3 | 3 |  |  | 3
| 44 | EA | REDUCER, ECC. - 12", 0.375" WT x 10", 0.365" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 30 | EA | ELL, 90 DEG - LR, 12", 0.375" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 31 | EA | ELL, 90 DEG - LR, 10", 0.365" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 32 | EA | ELL, 90 DEG - LR, 8", 0.322" WT, BW, MSS-SP-75, Y42, PER ASME B16.9 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 33 | EA | ELL, 90 DEG - LR, 6", 0.28" WT, BW, ASTM A234, WPB, PER ASME B16.9 | 4 |  | 4 |  | 0 | 8 | 0 | 8 |  |  | 4 | 4
| 34 | EA | ELL, 90 DEG - LR, 4", 0.237" WT, BW, ASTM A234, WPB, PER ASME B16.9 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 35 | EA | ELL, 90 DEG - LR, 2", 0.218" WT, BW, ASTM A234, WPB, PER ASME B16.9 | 3 |  | 3 |  | 0 | 6 | 0 | 6 |  |  | 3 | 3
| 36 | EA | ELL, 90 DEG - LR, 1 1/2", 0.200" WT, BW, ASTM A234, WPB, PER ASME B16.9 | 6 |  | 6 |  | 0 | 12 | 0 | 12 |  |  | 6 | 6
| 37 | EA | ELL, 45 DEG - 3R, 10", 0.365" WT, BW, MSS-SP-75, Y52, PER ASME B16.9 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 74 | EA | VALVE, PLUG - 1 1/2", ANSI 600, RF, API 6D, ASTM A216 WCB, REGULAR PATTERN, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LEVER OPERATED C/W LOCKING DEVICE, CLEANED AND PAINTED W/ SHOP PRIMER | 3 |  | 3 |  | 0 | 6 | 0 | 6 |  |  | 3 | 3
| 75 | EA | VALVE, BALL - 16", ANSI 600, RF, API 6D, FULL PORT, DOUBLE BLOCK & BLEED, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LESS LEVER FOR MOUNTING VALVE OPERATOR, CLEANED AND PAINTED W/ SHOP PRIMER | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 76 | EA | VALVE, BALL - 12", ANSI 600, RF, API 6D, FULL PORT, DOUBLE BLOCK & BLEED, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LESS LEVER FOR MOUNTING VALVE OPERATOR, CLEANED AND PAINTED W/ SHOP PRIMER | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 77 | EA | VALVE, BALL - 10", ANSI 600, RF, API 6D, FULL PORT, DOUBLE BLOCK & BLEED, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LESS LEVER FOR MOUNTING VALVE OPERATOR, CLEANED AND PAINTED W/ SHOP PRIMER | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 78 | EA | VALVE, BALL - 6", ANSI 600, RF, API 6D, FULL PORT, DOUBLE BLOCK & BLEED, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LEVER OPERATED, C/W LOCKING DEVICE, CLEANED AND PAINTED W/ SHOP PRIMER | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 79 | EA | VALVE, BALL - 4", ANSI 600, RF x WE, FULL PATTERN, API 6D, FULL PORT, LEVER OPERATED, C/W LOCKING DEVICE, TWT 4" OD, 0.237" WT, GRB PIPE | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 80 | EA | VALVE, BALL - 4", ANSI 600, RF, API 6D, FULL PORT, DOUBLE BLOCK & BLEED, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LEVER OPERATED, C/W LOCKING DEVICE, CLEANED AND PAINTED W/ SHOP PRIMER | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  |  | 1 | 1
| 81 | EA | VALVE, BALL - 2", ANSI 600, RF, API 6D, FULL PORT, DOUBLE BLOCK & BLEED, FOR SWEET NATURAL GAS SERVICE, -20°F TO 120°F, LEVER OPERATED, C/W LOCKING DEVICE, CLEANED AND PAINTED W/ SHOP PRIMER | 5 |  | 5 |  | 0 | 10 | 0 | 10 |  |  | 5 | 5
| 82 | EA | VALVE, BALL - 1", CLASS 3000, W.O.G., THRD, FNPT, C.S, SS TRIM, FULL PORT, NATURAL GAS SERVICE, C/W LEVER OPERATOR & LOCKING DEVICE | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 83 | EA | VALVE, BALL - 3/4", CLASS 3000, W.O.G., THRD, FNPT, C.S, SS TRIM, FULL PORT, NATURAL GAS SERVICE, C/W LEVER OPERATOR & LOCKING DEVICE | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  |  | 2 | 2
| 84 | EA | VALVE, BALL - 1/2", CLASS 3000, W.O.G., THRD, FNPT, C.S, SS TRIM, FULL PORT, NATURAL GAS SERVICE, C/W LEVER OPERATOR & LOCKING DEVICE | 3 |  | 3 |  | 0 | 6 | 0 | 6 |  |  | 3 | 3
| 85 | FT | VALVE, BALL - 1/4" BLAH BLAH |  | 4 |  |  | 0 | 4 | 0 | 0
| 56 | EA | WELDOLET - 2" ON 20", BW, MSS-SP-75, F60, BONNEY FORGE OR EQUAL, PER MSS SP-97, -20°F TO 250°F | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 57 | EA | WELDOLET - 2" ON 12", BW, MSS-SP-75, F52, BONNEY FORGE OR EQUAL, PER MSS SP-97, -20°F TO 250°F | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 58 | EA | WELDOLET - 1 1/2" ON 20", BW, MSS-SP-75, F60, BONNEY FORGE OR EQUAL, PER MSS SP-97, -20°F TO 250°F | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 59 | EA | WELDOLET - 1 1/2" ON 16", BW, MSS-SP-75, F52, BONNEY FORGE OR EQUAL, PER MSS SP-97, -20°F TO 250°F | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 60 | EA | THREDOLET - 24" - 14" x 1-1/2", CLASS 3000, FNPT ASTM A105, BONNEY FORGE OR EQUAL, PER MSS SP-97, -20°F TO 250°F | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 61 | EA | THREDOLET - 12" - 8" x 1-1/2", CLASS 3000, FNPT ASTM A105, BONNEY FORGE OR EQUAL, PER MSS SP-97, -20°F TO 250°F | 4 |  | 4 |  | 0 | 8 | 0 | 8 |  | 4 | 4
| 63 | EA | CLOSURE, HORIZONTAL - 20.000" OD, ANSI 600, TWT 0.500" WT, X60 PIPE, YALE OR EQUIV. | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 64 | EA | CLOSURE, HORIZONTAL - 12.750" OD, ANSI 600, TWT 0.375" WT, X52 PIPE, YALE OR EQUIV. | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 65 | EA | CLOSURE, HORIZONTAL - 4.500" OD, ANSI 600, TWT 0.237" WT, GR B PIPE, YALE OR EQUIV. | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 66 | EA | CLOSURE, HORIZONTAL - 2.375" OD, ANSI 600, TWT 0.218" WT, GR B PIPE, YALE OR EQUIV. | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 67 | EA | SADDLE, WELD 6" ON 20", 5/8" THK, HDR EDGE TAPERED TO 0.280", W/VENT HOLE, MSS-SP-75, Y65, PER FLEETLINE CATALOG SFI-105 & ASME B31.8 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 68 | EA | SADDLE, WELD 4" ON 12", 5/8" THK, HDR EDGE TAPERED TO 0.237", W/VENT HOLE, MSS-SP-75, Y52, PER FLEETLINE CATALOG SFI-105 & ASME B31.8 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 69 | EA | SADDLE, WELD 4" ON 10", 5/8" THK, HDR EDGE TAPERED TO 0.237", W/VENT HOLE, MSS-SP-75, Y52, PER FLEETLINE CATALOG SFI-105 & ASME B31.8 | 1 |  | 1 |  | 0 | 2 | 0 | 2 |  | 1 | 1
| 70 | EA | SADDLE, WELD 2" ON 20", 5/8" THK, HDR EDGE TAPERED TO 0.218", W/VENT HOLE, MSS-SP-75, Y65, PER FLEETLINE CATALOG SFI-105 & ASME B31.8 | 2 |  | 2 |  | 0 | 4 | 0 | 4 |  | 2 | 2
| 71 | EA | PLUG, HEXHEAD, 1", 3000#, MNPT, ASTM A105, PER ASME B16.11 | 2 |  | 2 |  | 2 | 6 | 1 | 5 | 1 |  | 2 | 2
| 72 | EA | PLUG, HEXHEAD, 3/4", 3000#, MNPT, ASTM A105, PER ASME B16.11 | 2 |  | 2 |  | 2 | 6 | 1 | 5 | 1 |  | 2 | 2
| 73 | EA | PLUG, HEXHEAD, 1/2", 3000#, MNPT, ASTM A105, PER ASME B16.11 | 3 |  | 3 |  | 2 | 8 | 1 | 7 | 1 |  | 3 | 3
| 86 | EA | GASKET, SPIRAL WOUND - 24", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR MSS-SP-44 FLANGE |  | 6 |  |  | 1 | 7 | 6 | 1 | 1
| 87 | EA | GASKET, SPIRAL WOUND - 16", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR MSS-SP-44 FLANGE | 4 |  | 4 |  | 1 | 9 | 0 | 9 | 1 |  | 4 | 4
| 88 | EA | GASKET, SPIRAL WOUND - 12", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR MSS-SP-44 FLANGE | 2 |  | 2 |  | 1 | 5 | 0 | 5 | 1 |  | 2 | 2
| 89 | EA | GASKET, SPIRAL WOUND - 10", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR MSS-SP-44 FLANGE | 4 |  | 4 |  | 1 | 9 | 0 | 9 | 1 |  | 4 | 4
| 90 | EA | GASKET, SPIRAL WOUND - 8", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR MSS-SP-44 FLANGE | 1 |  | 1 |  | 1 | 3 | 0 | 3 | 1 |  | 1 | 1
| 91 | EA | GASKET, SPIRAL WOUND - 6", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR ASME B16.5 FLANGE | 4 |  | 4 |  | 1 | 9 | 0 | 9 | 1 |  | 4 | 4
| 92 | EA | GASKET, SPIRAL WOUND - 4", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR ASME B16.5 FLANGE | 3 |  | 3 |  | 1 | 7 | 0 | 7 | 1 |  | 3 | 3
| 93 | EA | GASKET, SPIRAL WOUND - 2", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR ASME B16.5 FLANGE | 10 |  | 10 |  | 1 | 21 | 0 | 21 | 1 |  | 10 | 10
| 94 | EA | GASKET, SPIRAL WOUND - 1 1/2", ANSI 600, RF, FLEXITALLIC, STYLE CGI OR EQUAL, 304 SS WINDING WITH GRAPHITE FILLER, 304 SS OUTER & INNER RING, 1/8" THK, FOR ASME B16.5 FLANGE | 6 |  | 6 |  | 1 | 13 | 1 | 12 |  |  | 6 | 6